## Summary
| CONTRACTOR COST WORKBOOK: | Harrison Park Academy |  |  |  |  | #REF!
NAME OF CM FIRM
| ESTIMATED COST OF THE WORK: | 7556390
| CONSTRUCTION DELIVERY METHOD: | CMc | Construction Manager as Constructor
|  | Preconstruction |  | Construction |  |  |  |  | CMc | Construction Manager as Constructor
| START DATE: | 2027-01-05 |  | 2027-07-01 |  |  |  |  | CMa | Construction Manager as Advisor
| FINISH DATE: | 2027-06-30 |  | 2028-07-31 |  |  |  |  | DB | Design-Build, with GMP or Cost plus a Fee
[9 empty] | GC | General Contractor, with GMP or Cost plus a Fee
|  |  | Months | Weeks | Days |  |  |  | TBD | To be Determined
| PROJECT DURATION: | Pre-construction | 5.8667 | 25.1429 | 176
|  | Construction | 13.2 | 56.5714 | 396
| ESTIMATED BUILDING AREA: | 172739 |  | Sq. Ft.
GENERAL CONDITIONS RECAP SUMMARY
[5 empty] | EQ. & MATL. | LABOR | SUB-CON | TOTAL
| DESCRIPTION |  |  |  | TOTAL | TOTAL | TOTAL | COST
| PRECONSTRUCTION SERVICES |  |  |  | 0 | 400 | 0 | 400
| PRECONSTRUCTION SERVICES REIMBURSABLE EXPENSES |  |  |  | 0 |  | 0 | 0
| CONSTRUCTION PERSONNEL |  |  |  | 0 | 400 | 0 | 400
| CM REIMBURSABLES |  |  |  | 0 | 0 | 0 | 0
| PERMITS, INSURANCE & TAXES |  |  |  | 10 | 0 | 0 | 10
| TOTAL GENERAL CONDITIONS |  |  |  | 10 | 800 | 0 | 810
[7 empty] | GENERAL CONDITIONS AS % OF CONSTRUCTION COST = | 0.01072%
CONSTRUCTION MANAGER'S OVERHEAD & PROFIT (%) =
| Voluntary Alternate Add: | 0 | Project Managed Under Prevailing Wage Rules
[7 empty] | Preconstruction Hours: | 40
[7 empty] | Construction Hours: | 40
[7 empty] | TOTAL ESTIMATED CONSTRUCTION SERVICES AS % OF CONSTRUCTION COST = | 0.01072%
[7 empty] | TOTAL ESTIMATED CONSTRUCTION SERVICES COST = | 810
NOTES:
1. Personnel rates include the salaries of personnel and the portion of the cost of their mandatory and customary contributions and benefits related thereto, such as employment taxes and other statutory employee benefits, insurance, sick leave, holidays, vacations, pensions, and similar contributions and benefits. 2. Personnel rate increases are limited to three (3%) percent per year, after 12/31/2025. Hourly Rates shall be based on a forty (40) hour work week/salaried position and while the Construction Manager’s Personnel may work overtime, the Owner shall never be charged overtime rates. 3. General Liability Insurance may only be applied to Construction Manager’s Fee, and not the Cost of the Work

## Staff Hours
NAME OF CM FIRM | 0
Populate all staff and associated rates you intend to charge to the project. Add any staff you intend to charge.
SUMMARY OF STAFF HOURS
| Project Month (Overall) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
|  |  | 2024 | [5 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
|  |  | 2024-07-02 | 2024-08-02 | 2024-09-02 | 2024-10-02 | 2024-11-02 | 2024-12-02 | 2025-01-02 | 2025-02-02 | 2025-03-02 | 2025-04-03 | 2025-05-04 | 2025-06-05 | 2025-07-06 | 2025-08-07 | 2025-09-08 | 2025-10-09 | 2025-11-10 | 2025-12-11 | 2026-01-02 | 2026-02-02 | 2026-03-02 | 2026-04-03 | 2026-05-04 | 2026-06-05 | 2026-07-06 | 2026-08-06 | 2026-09-06 | 2026-10-06 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01
|  |  | 2024-07-02: Pre-Construction Phase Project Hours | Pre-Construction
Personnel/Name | Function | Hourly Rate | [40 empty] | Hours | Cost
| Project Exec. | 0 | [40 empty] | 0 | 0
Joe 'Example' Dirt | Sr. Proj. Mgr. | 10 | [40 empty] | 40 | 400 | bar: 2024-07-02 to 2027-10-01
| Proj. Mgr. 1 | 0 | [40 empty] | 0 | 0
| Pre-Con Mgr. | 0 | [40 empty] | 0 | 0
| Sr. Estimator | 0 | [40 empty] | 0 | 0
| Estimator 1 | 0 | [40 empty] | 0 | 0
| Mech. Est. | 0 | [40 empty] | 0 | 0
| Elect. Est. | 0 | [40 empty] | 0 | 0
| Scheduler | 0 | [40 empty] | 0 | 0
| Proj. Supt. | 0 | [40 empty] | 0 | 0
| Accountant | 0 | [40 empty] | 0 | 0
| Admin. Asst. | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
| Pre-Construction Hours: | [41 empty] | 40 | 400 | bar: 2024-07-02 to 2027-10-01
Construction Months
|  |  | 2024-07-02: Construction Phase Project Hours | Construction
Personnel/Name | Function | Hourly Rate | [40 empty] | Hours | Cost
| Project Exec. | 0 | [40 empty] | 0 | 0
Joe 'Example' Dirt | Sr. Proj. Mgr. | 10 | [40 empty] | 40 | 400 | bar: 2024-07-02 to 2027-10-01
| Proj. Mgr. 1 | 0 | [40 empty] | 0 | 0
| Proj. Mgr. 2 | 0 | [40 empty] | 0 | 0
| Proj. Mgr. 3 | 0 | [40 empty] | 0 | 0
| Proj. Mgr. 4 | 0 | [40 empty] | 0 | 0
| Proj. Engr. 1 | 0 | [40 empty] | 0 | 0
| Proj. Engr. 2 | 0 | [40 empty] | 0 | 0
| Proj. Engr. 3 | 0 | [40 empty] | 0 | 0
| Proj. Engr. 4 | 0 | [40 empty] | 0 | 0
| Safety Engr. | 0 | [40 empty] | 0 | 0
| General Supt. | 0 | [40 empty] | 0 | 0
| Proj. Supt. 1 | 0 | [40 empty] | 0 | 0
| Proj. Supt. 2 | 0 | [40 empty] | 0 | 0
| Proj. Supt. 3 | 0 | [40 empty] | 0 | 0
| Proj. Supt. 4 | 0 | [40 empty] | 0 | 0
| Accountant | 0 | [40 empty] | 0 | 0
| Admin. Asst. | 0 | [40 empty] | 0 | 0
| Expeditor | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
|  | 0 | [40 empty] | 0 | 0
| Construction Hours: | [41 empty] | 40 | 400 | bar: 2024-07-02 to 2027-10-01

## Construction Support
|  | NAME OF CM FIRM | 0
|  |  | Preconstruction |  | Construction
|  | START DATE: | 2027-01-05 |  | 2027-07-01
|  | FINISH DATE: | 2027-06-30 |  | 2028-07-31
Populate all categories you intend to charge to the project. Add any other costs you intend to charge.
|  |  |  | Months | Weeks | Days
|  | PROJECT DURATION: | Pre-construction | 5.8667 | 25.1429 | 176
|  |  | Construction | 13.2 | 56.5714 | 396
| CODE | DESCRIPTION | QTY. | UNIT | UNIT | (E) EQUIP. & |  | (S) SUB- | TOTAL
| NO. |  |  |  | PRICE | MAT'L | (L) LABOR | CONTRACTOR | COST
CM REIMBURSABLES
E |  | TEMPORARY TOILETS - 1 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | TEMPORARY TOILETS - 2 |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | TEMPORARY FENCE |  | MO |  | 0 | 0 | 0 | 0 | TRUE
E |  | DUMPSTERS |  | LS |  | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
[6 empty] | 0 | 0 | 0 | 0 | TRUE
|  | CM REIMBURSABLES TOTAL |  |  |  | 0 | 0 | 0 | 0
PERMITS, INSURANCE & TAXES
E |  | BUILDING PERMIT | 1 | LS | 10 | 10 | 0 | 0 | 10 | TRUE
E |  | SPECIAL PERMITS |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | SPECIAL FEES |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | SITE PLAN REVIEW |  | LS |  | 0 | 0 | 0 | 0 | TRUE
E |  | BUILDERS RISK INSURANCE |  | LS |  | 0 | 0 | 0 | 0 | TRUE
|  | 100% PLM Bond |  | % |  | 0 | 0 | 0 | 0 | TRUE
E |  | GENERAL LIABILITY INSURANCE |  | LS |  | 0 | 0 | 0 | 0 | TRUE
|  | PERMITS, INSURANCE & TAXES TOTAL |  |  |  | 10 | 0 | 0 | 10
SUMMARY & ERROR CHECK
|  | LABOR SUBTOTAL: | 0 | TRUE
|  | TOTAL: | 10 | FALSE

## Staff Cashflow
NAME OF CM FIRM | 0
STAFFING CASHFLOW
| Project Month (Overall) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
|  |  | 2024 | [11 empty] | 2025
|  |  | 2024-01-20 | 2024-02-20 | 2024-03-20 | 2024-04-20 | 2024-05-20 | 2024-06-20 | 2024-07-20 | 2024-08-20 | 2024-09-20 | 2024-10-20 | 2024-11-20 | 2024-12-20 | 2025-01-20 | 2025-02-20 | 2025-03-20
|  |  | 2024-01-20: Pre-Construction Phase Project Hours | [10 empty] | Pre-Construction
Personnel | Function | Hrly Rate | [25 empty] | Hours | Cost
0 | Project Exec. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Joe 'Example' Dirt | Sr. Proj. Mgr. | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 40 | 400
0 | Proj. Mgr. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Pre-Con Mgr. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Sr. Estimator | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Estimator 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Mech. Est. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Elect. Est. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Scheduler | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Accountant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Admin. Asst. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Pre-Con Staff Costs: |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 40 | 400
Construction Months
|  |  | 2024-01-20: Construction Phase Project Hours | [10 empty] | Construction
Personnel | Function | Hrly Rate | [25 empty] | Hours | Cost
0 | Project Exec. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Joe 'Example' Dirt | Sr. Proj. Mgr. | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 40 | 400
0 | Proj. Mgr. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Mgr. 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Mgr. 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Mgr. 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Engr. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Engr. 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Engr. 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Engr. 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Safety Engr. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | General Supt. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Proj. Supt. 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Accountant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Admin. Asst. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | Expeditor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction Staff Costs: |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 40 | 400
| Staff Cost Cashflow: |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 80 | 800